## Projects_Master
Project Name | Owner | Start Date | Target Date | Current Sprint | Overall Progress % | Frontend % | Backend % | Database % | Testing % | Deployment % | Current Status | Health Status | Expected Completion
SmartKhata | Adesh/Dev Team | 2026-06-23 | 2026-09-18 | Sprint 2 | 64 | 76 | 74 | 68 | 18 | 0 | In Progress | Yellow | 2026-09-18

## Daily_Updates
Date | Developer | Project | Sprint | Page | Module | Submodule | Task ID | Task Description | Frontend Status | Backend Status | Database Status | API Status | Testing Status | Priority | Estimated Hours | Actual Hours | Completion % | Current Status | Blockers | Start Date | Target Date | Remarks
2026-06-23 | Adesh/Dev Team | SmartKhata | Sprint 1 | Project Management | Planning | Baseline | SK-PM-001 | Created project management sheets and Excel workbook | Done | Done | No Change | No Change | Manual baseline | High | 4 | 4 | 100 | Done | None | 2026-06-23 | 2026-06-23 | Baseline exported to Excel
2026-06-24 | Adesh/Dev Team | SmartKhata | Sprint 1 | Inventory | Collections Rename | Inventory module | SK-002 | Replaced Collections page with Inventory page and backward-compatible /collections route | Done | Done | Done | Done | Build Passed | High | 7 | 7 | 90 | QA | Manual database testing pending | 2026-06-24 | 2026-06-25 | Collections.jsx/CSS removed; Inventory.jsx/CSS added
2026-06-24 | Adesh/Dev Team | SmartKhata | Sprint 1 | Dashboard | Analytics | Live dashboard aggregation | SK-001 | Connected dashboard with customers, credits, payments, orders and inventory data | Done | Partial | No Change | Integrated | Build Passed | High | 8 | 8 | 75 | In Progress | Fallback mock values still present | 2026-06-24 | 2026-06-25 | Production build verified
2026-06-25 | Adesh/Dev Team | SmartKhata | Sprint 1 | Customers | Customer Ledger | Customer detail and product entry | SK-005 | Enhanced customer page with summary cards, selected customer panel, product entry and unified history | Done | Done | Done | Done | Build Passed | High | 8 | 8 | 85 | QA | Needs manual CRUD/history verification with MySQL | 2026-06-24 | 2026-06-25 | Customer history includes payments, product entries and shopping orders
2026-06-25 | Adesh/Dev Team | SmartKhata | Sprint 1 | Shopping | Shopping Orders | Product catalog and order board | SK-006 | Improved shopping page UI, product CRUD, order filters/status and product preview modal | Done | Done | Done | Done | Build Passed | High | 7 | 7 | 80 | QA | Manual order flow testing pending | 2026-06-24 | 2026-06-25 | Orders functional inside Shopping page
2026-06-30 | Adesh/Dev Team | SmartKhata | Sprint 2 | Orders | Standalone Orders | Order management screen | SK-W2-002 | Built full Orders page with summary cards, order search/filter, status updates, product list and refresh | Done | Done | No Change | Integrated | Build Passed | High | 8 | 7 | 85 | QA | Manual DB order status testing pending | 2026-06-30 | 2026-06-30 | Orders page no longer placeholder
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | Staff | Staff Management | Staff CRUD and staff finance APIs | SK-W2-006 | Added Staff module with frontend page, sidebar route, backend staff CRUD, summary, attendance, salary payment and advance APIs | Done | Done | Done | Done | Build Passed | High | 10 | 9 | 78 | In Progress | Attendance/salary/advance frontend screens pending | 2026-07-01 | 2026-07-01 | Core staff CRUD UI done; advanced staff APIs exist
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | Supplier/Credit | Architecture Split | Supplier purchases and customer credits | SK-W2-007 | Split old credit module into supplier-purchases and customer-credits APIs/services; updated supplier route to /supplier | Done | Done | Done | Done | Build Passed | High | 7 | 6 | 82 | QA | Manual old route regression pending | 2026-07-01 | 2026-07-01 | Old Credit.jsx/Credit.css and creditRoutes removed
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | Customers | Customer Product Entries | Edit/delete product entry support | SK-W2-008 | Added customer product entry update/delete service and route support | Partial | Done | Done | Done | Build Passed | Medium | 5 | 3 | 65 | In Progress | Need confirm UI exposes edit/delete actions | 2026-07-01 | 2026-07-02 | Backend/service ready
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | All | Build Verification | Frontend production build | SK-QA-001 | Ran frontend production build after Staff/Orders/Supplier changes | Done | No Change | No Change | No Change | Passed | High | 1 | 1 | 100 | Done | None | 2026-07-01 | 2026-07-01 | vite build passed with 117 modules
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | Transactions | Unified Ledger | Transactions page/API | SK-W2-003 | Implement active Transactions route/page and backend unified transaction API | Pending | Pending | Pending | Pending | Pending | High | 8 | 0 | 0 | To Do | Route not active in sidebar/app | 2026-07-02 | 2026-07-03 | Still placeholder file only
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | Reports | Reports | Business reports | SK-W2-004 | Build Reports page with filters and export-ready summaries | Pending | Pending | Pending | Pending | Pending | High | 8 | 0 | 0 | To Do | Depends report data contract | 2026-07-03 | 2026-07-05 | Still placeholder
2026-07-01 | Adesh/Dev Team | SmartKhata | Sprint 2 | Settings | Settings | App settings | SK-008 | Create settings page for shop/profile/security/config | Pending | Pending | Pending | Pending | Pending | Medium | 6 | 0 | 0 | To Do | Scope not finalized | 2026-07-04 | 2026-07-06 | Still placeholder

## Daily_Task_Planner
Task ID | Today's Tasks | Tomorrow Tasks | Day After Tomorrow Tasks | Estimated Hours | Priority | Dependencies | Status
SK-W2-006 | 01 Jul: Complete Staff CRUD verification and fix form/backend mismatches | 02 Jul: Add attendance/salary/advance UI panels | 03 Jul: QA staff history and summary totals | 8 | High | Staff backend APIs | In Progress
SK-W2-008 | 01 Jul: Verify customer product entry edit/delete service and route | 02 Jul: Add edit/delete controls in Customers UI if missing | 03 Jul: Regression test customer balances | 5 | Medium | Customer product entry API | In Progress
SK-W2-003 | 02 Jul: Activate Transactions route and unified backend transaction API | 03 Jul: Add transaction filters/search | 04 Jul: Use data in Reports page | 8 | High | Payments, credits, product entries, orders | To Do
SK-W2-004 | 03 Jul: Build Reports foundation with summary cards and date filters | 04 Jul: Add CSV-ready table | 05 Jul: Validate totals | 8 | High | SK-W2-003 or direct module APIs | To Do
SK-QA-002 | 01 Jul: Run frontend build and smoke checklist | 02 Jul: Manual API checks in MySQL | 03 Jul: Update release readiness | 4 | High | Core module stability | In Progress

## Weekly_Roadmap
Week Number | Feature | Page | Module | Owner | Planned Hours | Actual Hours | Dependencies | Target Date | Completion % | Status | Remarks
Week 1 | Core stabilization and UX upgrade | Dashboard/Customers/Inventory/Shopping | Core ledger and stock | Adesh/Dev Team | 38 | 36 | Existing APIs | 2026-06-29 | 75 | QA | Major UI and data integration completed; manual DB QA pending
Week 2 - 2026-06-29 | Core QA stabilization | Customers/Inventory/Shopping/Payment | QA and defect fixing | Adesh/Dev Team | 8 | 0 | Local MySQL test data | 2026-06-29 | 40 | In Progress | Some core flows updated; formal manual QA still pending
Week 2 - 2026-06-30 | Standalone Orders implementation | Orders | Order management | Adesh/Dev Team | 8 | 7 | Shopping orders API | 2026-06-30 | 85 | QA | Orders page implemented with filters, summary and status update
Week 2 - 2026-07-01 | Staff and credit architecture | Staff/Supplier/Customer Credits | Staff + credit split | Adesh/Dev Team | 10 | 9 | Staff API and split credit APIs | 2026-07-01 | 78 | In Progress | Staff core CRUD added; supplier/customer credit APIs split
Week 2 - 2026-07-02 | Unified transactions | Transactions/API | Ledger consolidation | Adesh/Dev Team | 8 | 0 | Payments, customer credits, product entries, orders | 2026-07-02 | 0 | Planned | Activate route and build unified transaction data contract
Week 2 - 2026-07-03 | Reports and release readiness | Reports/All | Reporting and QA | Adesh/Dev Team | 8 | 0 | Transaction/report data sources | 2026-07-03 | 0 | Planned | Reports foundation, smoke checklist, final build
Week 3 | Settings and auth hardening | Settings/Auth/Security | User/account config | Adesh/Dev Team | 36 | 0 | JWT middleware and route protection | 2026-07-13 | 0 | Planned | Protect routes/APIs and move credentials to env
Week 4 | Testing and release prep | All | QA/DevOps | Adesh/Dev Team | 40 | 2 | Feature freeze | 2026-07-20 | 8 | Planned | Frontend build passes; automated tests still missing
Month 2 | Advanced reporting/export/mobile polish | Reports/Dashboard | Analytics | Adesh/Dev Team | 120 | 0 | Month 1 MVP | 2026-08-21 | 0 | Planned | CSV/PDF/export and UX polish
Month 3 | Production readiness | All | Scale/security/deployment | Adesh/Dev Team | 120 | 0 | Month 2 complete | 2026-09-18 | 0 | Planned | Monitoring, backups, CI/CD, roles

## Sprint_Tracker
Sprint | Features | Completed | In Progress | Pending | Bugs | Testing Status | Release Readiness | Health Status
Sprint 1 | Dashboard live data, customer ledger upgrade, inventory split, shopping UX | 3 | 3 | 2 | 6 | Build Passed / Manual QA Pending | 48% | Yellow
Sprint 2 | Orders implementation, Staff module, supplier/customer credit split, transactions/reports next | 2 | 3 | 3 | Known open bugs tracked | Build Passed / Manual QA Pending | 50% | Yellow
Sprint 3 | Settings, auth hardening, environment/security cleanup | 0 | 0 | 5 | Unknown | Not Started | 8% | Yellow
Sprint 4 | Automated tests, deployment, release candidate | 0 | 0 | 6 | Unknown | Build only | 8% | Red

## Feature_Tracker
Feature | Frontend | Backend | Database | API | Testing | Deployment | Overall Status | Completion %
Authentication | 70 | 65 | 50 | 60 | 10 | 0 | In Progress | 60
Customer Ledger | 88 | 86 | 78 | 86 | 22 | 0 | In Progress | 82
Payments | 74 | 78 | 70 | 78 | 18 | 0 | In Progress | 72
Supplier Purchases | 86 | 84 | 78 | 85 | 20 | 0 | QA | 82
Customer Credits | 55 | 78 | 70 | 78 | 12 | 0 | In Progress | 58
Inventory / Collections | 90 | 84 | 84 | 86 | 22 | 0 | QA | 84
Shopping Products | 84 | 80 | 76 | 80 | 20 | 0 | QA | 78
Orders | 86 | 80 | 76 | 80 | 22 | 0 | QA | 82
Staff Management | 78 | 86 | 80 | 86 | 18 | 0 | In Progress | 78
Dashboard | 78 | 25 | 0 | 72 | 18 | 0 | In Progress | 68
Transactions | 5 | 0 | 0 | 0 | 0 | 0 | Not Started | 5
Reports | 5 | 0 | 0 | 0 | 0 | 0 | Not Started | 5
Settings | 5 | 0 | 0 | 0 | 0 | 0 | Not Started | 5
Project Management | 100 | 0 | 0 | 0 | 100 | 0 | Done | 100

## Frontend_Tracker
Page | Module | Components | Framework | Status | Completion %
Register | Authentication | Register form | React/Vite | In Progress | 70
Login | Authentication | Login form | React/Vite | In Progress | 70
Dashboard | Analytics | Live summary cards, recent transactions, quick actions, amount donut, top products, low stock alerts | React/Vite | In Progress | 78
Customers | Customer Ledger | Summary cards, customer list, detail panel, product entry, history table | React/Vite | In Progress | 88
AddCustomer | Customer Ledger | Add/edit customer form | React/Vite | In Progress | 78
Supplier | Supplier Purchases | Supplier purchase form, summary cards, table, edit/delete | React/Vite | QA | 86
Payment | Payments | Payment form, table, summary, trend and top customer blocks | React/Vite | In Progress | 74
Shopping | Shopping Products | Product catalog, product CRUD, filters, preview modal | React/Vite | QA | 84
Orders | Shopping Orders | Order summary, search/filter, order cards, status updates | React/Vite | QA | 86
Inventory | Inventory | Stock summary, product CRUD, stock update, low stock alerts, history table | React/Vite | QA | 90
Staff | Staff Management | Staff summary, add/edit/delete form, searchable staff list, staff profile | React/Vite | In Progress | 78
Collections | Inventory Alias | Route maps to Inventory | React/Vite | Replaced | 90
Transactions | Ledger | Placeholder only, not active route | React/Vite | Not Started | 5
Reports | Reports | Placeholder | React/Vite | Not Started | 5
Settings | Settings | Placeholder | React/Vite | Not Started | 5
Sidebar | Navigation | Dashboard, Customers, Supplier, Payment, Shopping, Inventory, Staff, Orders, Reports, Settings | React/Vite | Done | 95

## Backend_Tracker
Service | Controller | Business Logic | Middleware | Authentication | Status | Completion %
Auth | authController | Register, login, JWT | None | JWT generation | In Progress | 65
Customers | customerController | CRUD, product entries, update/delete product entries, payment/order/product history merge | None | Not enforced | In Progress | 86
Payments | paymentController | CRUD, summary, balance updates, trends/top/recent data | None | Not enforced | In Progress | 78
Customer Credits | customerCreditController | Customer credit CRUD | None | Not enforced | In Progress | 78
Supplier Purchases | supplierPurchaseController | Supplier purchase CRUD, summary and pending calculations | None | Not enforced | QA | 84
Suppliers | supplierController | Legacy supplier table CRUD still present | None | Not enforced | Partial | 60
Shopping | shoppingController | Product/order CRUD, order status, stock updates | None | Not enforced | QA | 80
Inventory / Collections | collectionController | Product stock CRUD, summary, stock movements, seed/sample products | None | Not enforced | QA | 84
Staff | staffController | Staff CRUD, summary, attendance, salary payments, advance payments, history | None | Not enforced | In Progress | 86
Transactions | transactionController | No implementation found | None | Not enforced | Not Started | 0
Server Routes | server.js | /customer-credits, /supplier-purchases, /staff, /inventory and compatibility routes mounted | CORS/JSON | Not enforced | Done | 90

## Database_Tracker
Table | Relationships | Indexes | Migration | Seed Data | Completion %
users | Auth users | Needs review | Implicit/unknown | No | 50
customers | Customer ledger | Needs review | Implicit/unknown | No | 70
customer_product_entries | Customer history and pending balance | customer_id relationship | Controller creates table | No | 82
payments | Customer balance updates and dashboard summaries | customer_id relationship | Controller creates table | No | 72
customer_credits | Customer credit | Needs review | Controller creates table | No | 70
supplier_purchases | Supplier debit and pending balance | Needs review | Controller creates/updates table | No | 78
suppliers | Legacy supplier records | Needs review | Controller creates table | No | 55
products | Shopping and inventory shared product table | Primary key | Schema file and controller | Yes | 86
stock_movements | Product stock history | product_id relationship | Schema file and controller | Opening stock | 84
shopping_orders | Order header | Needs review | Schema file and controller | No | 78
shopping_order_items | Order lines | order_id/product_id relationship | Schema file and controller | No | 78
staff | Staff profile records | Primary key | Controller creates/updates table | No | 80
staff_attendance | Staff attendance history | unique_staff_attendance | Controller creates table | No | 70
staff_salary_payments | Staff salary payments | staff_id relationship | Controller creates table | No | 70
staff_advances | Staff advances | staff_id relationship | Controller creates table | No | 70
migrations | Central migration workflow | Missing | Split between controllers and SQL file | Partial | 30

## API_Tracker
API Name | Endpoint | Method | Integrated | Testing Status | Completion %
Register | /api/auth/register | POST | Yes | Build only | 60
Login | /api/auth/login | POST | Yes | Build only | 60
Customers | /api/customers | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 86
Customer History | /api/customers/:id/history | GET | Yes | Build passed; manual pending | 86
Customer Product Entry | /api/customers/:id/product-entry | POST | Yes | Build passed; manual pending | 84
Customer Product Entry Update | /api/customers/:id/product-entry/:entryId | PUT | Service/route ready | Build passed; UI pending check | 75
Customer Product Entry Delete | /api/customers/:id/product-entry/:entryId | DELETE | Service/route ready | Build passed; UI pending check | 75
Payments | /api/payments | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 78
Payment Summary | /api/payments/summary | GET | Yes | Build passed; manual pending | 80
Customer Credits | /api/customer-credits | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 78
Supplier Purchases | /api/supplier-purchases | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 84
Supplier Purchase Summary | /api/supplier-purchases/summary | GET | Yes | Build passed; manual pending | 84
Suppliers Legacy | /api/suppliers | GET/POST/PUT/DELETE | Partial | Manual pending | 60
Shopping Products | /api/shopping/products | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 80
Shopping Orders | /api/shopping/orders | GET/POST | Yes | Build passed; manual pending | 80
Shopping Order Status | /api/shopping/orders/:id/status | PATCH | Yes | Build passed; manual pending | 82
Staff Summary | /api/staff/summary | GET | Yes | Build passed; manual pending | 86
Staff CRUD | /api/staff | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 84
Staff History | /api/staff/:id/history | GET | Service ready | Build passed; UI pending | 72
Staff Attendance | /api/staff/:id/attendance | POST | Service ready | Build passed; UI pending | 70
Staff Salary Payments | /api/staff/:id/salary-payments | POST | Service ready | Build passed; UI pending | 70
Staff Advances | /api/staff/:id/advances | POST | Service ready | Build passed; UI pending | 70
Inventory Products | /api/inventory/products | GET/POST/PUT/DELETE | Yes | Build passed; manual pending | 86
Inventory Stock Update | /api/inventory/products/:id/stock | PATCH | Yes | Build passed; manual pending | 86
Inventory History | /api/inventory/history | GET | Yes | Build passed; manual pending | 86
Inventory Summary | /api/inventory/summary | GET | Yes | Build passed; manual pending | 86
Collections Compatibility | /api/collections/* | GET/POST/PUT/PATCH/DELETE | Yes | Build passed; manual pending | 82
Transactions | /api/transactions | GET | No | Not started | 0

## Bug_Tracker
Bug ID | Module | Severity | Assigned To | ETA | Status
BUG-001 | Dashboard still contains fallback mock totals/transactions when APIs return empty | Medium | Adesh/Dev Team | 2026-07-03 | Open
BUG-002 | Transactions route/API not active despite placeholder file | Medium | Adesh/Dev Team | 2026-07-04 | Open
BUG-003 | Reports and settings are placeholders | Medium | Adesh/Dev Team | 2026-07-06 | Open
BUG-004 | No automated unit/integration tests | High | Adesh/Dev Team | 2026-07-15 | Open
BUG-005 | Hardcoded database credentials in backend config | High | Adesh/Dev Team | 2026-07-10 | Open
BUG-006 | ProtectedRoute/auth middleware not consistently applied | High | Adesh/Dev Team | 2026-07-10 | Open
BUG-007 | Staff attendance/salary/advance APIs exist but frontend forms/history are not implemented | Medium | Adesh/Dev Team | 2026-07-05 | Open
BUG-008 | Root package/node_modules added outside frontend/backend; dependency ownership should be cleaned | Low | Adesh/Dev Team | 2026-07-05 | Open
BUG-009 | Some UI strings show encoding artifacts for rupee/icons in terminal view | Low | Adesh/Dev Team | 2026-07-05 | Open
BUG-010 | Staff frontend includes employee_id/email/department fields but backend currently persists only name/mobile/role/salary/date/status/address/note | Medium | Adesh/Dev Team | 2026-07-03 | Open

## Testing_Tracker
Feature | Unit Test | Integration Test | Manual Test | UAT | Status
Authentication | Pending | Pending | Pending | Pending | Not Started
Customer Ledger | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Payments | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Supplier Purchases | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Customer Credits | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Inventory / Collections | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Shopping Products | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Orders | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Staff | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Dashboard | Pending | Pending | Pending | Pending | Build Passed / Manual QA Pending
Transactions | Pending | Pending | Pending | Pending | Not Started
Reports | Pending | Pending | Pending | Pending | Not Started
Settings | Pending | Pending | Pending | Pending | Not Started
Frontend Build | Not Applicable | Not Applicable | Passed | Not Applicable | Passed on 2026-07-01

## Deployment_Tracker
Environment | Frontend Version | Backend Version | Database Version | Status
Local Development | 0.0.0 | 1.0.0 | adesh local MySQL | Available
Frontend Production Build | 0.0.0 | Not applicable | Not applicable | Passed on 2026-07-01
Staging | Not assigned | Not assigned | Not assigned | Not Started
Production | Not assigned | Not assigned | Not assigned | Not Started
Database Backup | Not applicable | Not applicable | Not configured | Not Started
CI/CD | Not configured | Not configured | Not configured | Not Started

## Risks_And_Blockers
Risk Type | Description | Severity | Owner | Mitigation Plan | Status
Testing | No automated tests found; only frontend build verified | High | Adesh/Dev Team | Add frontend smoke tests and backend API integration tests | Open
Security | Hardcoded MySQL password in backend config | High | Adesh/Dev Team | Move credentials to .env and rotate local password if needed | Open
Security | JWT middleware exists but APIs are not protected consistently | High | Adesh/Dev Team | Apply auth middleware to protected routes and frontend routes | Open
Scope | Reports, settings and transactions remain incomplete | Medium | Adesh/Dev Team | Implement after Staff/Orders QA | Open
Scope | Staff advanced workflows have backend APIs but frontend forms/history are pending | Medium | Adesh/Dev Team | Add attendance, salary, advance and history UI sections | Open
Data | Database migrations are split between controllers and SQL file | Medium | Adesh/Dev Team | Create controlled migration scripts | Open
Dependency | Root package/node_modules introduced outside frontend/backend structure | Low | Adesh/Dev Team | Move required dependencies into owning package and ignore node_modules | Open
Data Quality | Dashboard still falls back to mock values when data is empty | Medium | Adesh/Dev Team | Add backend summary endpoint and empty-state UI | Open
Data Model | Staff form fields employee_id/email/department are not persisted by backend schema | Medium | Adesh/Dev Team | Add backend columns or remove frontend fields | Open

## Team_Productivity
Developer | Tasks Completed | Hours Worked | Productivity Score | Remarks
Adesh/Dev Team | 8 | 58 | High | Dashboard, Customers, Inventory, Shopping, Orders, Staff, Supplier split and project management updates progressed through 2026-07-01

## Daily_Report
Completed Tasks | Tasks In Progress | Pending Tasks | Blockers | Bug Fixes | Hours Worked | Today's Progress % | Overall Project % | Tomorrow's Deliverables | Health Status
Project baseline Excel; Inventory replacement; Dashboard live aggregation; Customers page upgrade; Shopping UI/order board upgrade; standalone Orders page; Staff core module; supplier/customer credit API split; frontend build verification on 2026-07-01 | Staff advanced UI; customer product entry edit/delete UI check; dashboard fallback cleanup; manual QA | Transactions route/API; Reports; Settings; automated tests; deployment/security hardening | No automated tests; hardcoded DB config; reports/settings/transactions placeholders; manual MySQL QA pending; Staff form/backend field mismatch | Orders placeholder resolved; Credit module split; Staff module added; shopping service moved to services; inventory service moved to services | 58 | 14 | 64 | Transactions API/page, Staff advanced UI alignment, Reports foundation | Yellow

## Weekly_Report
Week 1 Summary | Week 2 Summary | Completed Features | Pending Features | Delays | Dependencies | Risks | Testing Status | Overall Completion % | Expected Completion Date | Health Status
Major UI/data work completed for Dashboard, Customers, Inventory and Shopping; project reports refreshed | Orders implemented; Staff module added; supplier/customer credit architecture split; frontend build passed on 2026-07-01 | Project management baseline, Inventory module, Dashboard integration, Customer ledger upgrade, Shopping UX, Orders page, Staff core CRUD, Supplier purchase split | Transactions, Reports, Settings, Staff advanced frontend, automated tests, deployment/security hardening | Transactions and Reports still behind original Week 2 plan | MySQL local schema, manual API verification, unified transaction data contract, auth route policy | No automated tests, hardcoded DB password, dashboard fallback data, Staff field persistence mismatch | Frontend production build passed; manual QA pending | 64 | 2026-09-18 | Yellow

## Release_Report
Frontend Completion % | Backend Completion % | Database Completion % | API Completion % | Testing Completion % | Deployment Completion % | Security Status | Performance Optimization | CI/CD Status | Known Issues | Release Readiness % | Confidence Level % | Ready For Deployment
76 | 74 | 68 | 75 | 18 | 0 | Needs hardening | Vite production build passed; no performance audit | Not started | Reports/settings/transactions incomplete; no automated tests; hardcoded DB config; dashboard fallbacks; Staff advanced UI pending; Staff field persistence mismatch; manual DB QA pending | 50 | 65 | NO